## Summary
BUG REPORT — SDCMS
Supply & Delivery Chain Management System ¦ Testing Cycle: May – June 2026
PROJECT INFORMATION
Project Name |  | SDCMS – Supply & Delivery Chain Management System
Project Version |  | 1.0 (Initial Release)
Platform |  | Web (Browser) + Mobile Application
Test Environment |  | Staging / UAT
Prepared By |  | Vaishnavi
Testing Period |  | 12 May 2026 – 29 May 2026
Report Date |  | 2026-05-01
Total Bugs Filed |  | 42 (35 Web + 7 App)
Total Bugs Closed |  | 42 — All Resolved ✓
DEFECT SUMMARY
Platform | Issues Found | Retested | Closed | Open | Pass Rate
Web (Browser) | 35 | 35 | 35 | 0 | 100%
Mobile App | 7 | 7 | 7 | 0 | 100%
TOTAL | 42 | 42 | 42 | 0 | 100%
PRIORITY LEGEND
🔴 HIGH – Critical / Blocking |  | 🟡 MEDIUM – Significant |  | 🟢 LOW – Minor / Cosmetic
TESTING NOTES
• All 42 defects have been resolved and retested. Current open count: 0.
• Modules tested: Login, Dashboard, Employee Mgmt, Product Catalogue, Courier Master, Order List, Create Order, Bulk Upload/Order, Recent Scans, Print Label, Mobile App.
• Issue types: functional bugs, UI/UX gaps, API integration failures, missing features, RBAC issues.
• Role-based access control (RBAC) was a recurring concern — fully resolved as of 25-05-26.

## Web Issues
SDCMS – Web Issue Log (35 Issues — All Closed)
Total: 35 ¦ High: 23 ¦ Medium: 9 ¦ Low: 3 ¦ Status: All Closed
# | Bug ID | Date Reported | Description / Summary | Priority | Assigned To | Fixed By | Reported By | Status | Updated On
1 | I001 | 13-05-26 | Login – Forgot Password functionality missing | High | Aditya B, Swati | — | Vaishnavi | Closed | —
2 | I002 | 13-05-26 | Dashboard – System Administrator profile shows null for mobile number and role | High | Swati | Swati | Vaishnavi | Closed | 13-05-26
3 | I003 | 13-05-26 | Employee Management – Allow Login checkbox not working; also affects Product Catalogue, Courier Master | High | Aditya B | Aditya B, Swati | Vaishnavi | Closed | 19-05-26
4 | I004 | 13-05-26 | Product Catalogue – Add New Product is not working | High | Aditya B, Swati | Aditya B | Vaishnavi | Closed | 16-05-26
5 | I005 | 13-05-26 | Enable/Disable field missing in Product Catalogue, Courier Master, and Employee Management | High | Aditya B, Swati | Aditya B, Swati | Vaishnavi | Closed | 19-05-26
6 | I006 | 13-05-26 | Order List – Order Status dropdown not working (frontend issue) | High | Swati | Swati | Vaishnavi | Closed | 20-05-26
7 | I007 | 13-05-26 | Order List – Print Label field shows null data | High | Aditya B, Swati | Swati | Vaishnavi | Closed | 13-05-26
8 | I008 | 13-05-26 | Order List – Send Notification and Mark as Dispatched actions not working | High | Swati, Aditya B | Aditya B | Vaishnavi | Closed | 20-05-26
9 | I009 | 13-05-26 | Order List – Order details not showing total amount after adding quantity | High | Swati | Swati | Vaishnavi | Closed | 13-05-26
10 | I010 | 13-05-26 | Order List – Courier Partner field is null | High | Aditya B, Swati | Aditya B | Vaishnavi | Closed | —
11 | I011 | 13-05-26 | Order List – Remove Send Notification and Mark as Dispatched from Action button (handled via feature flag) | High | Aditya B, Swati | Aditya B, Swati | Vaishnavi | Closed | 20-05-26
12 | I012 | 13-05-26 | Create Order – Total amount not updating after adding product quantity | High | Aditya B, Swati | Swati | Vaishnavi | Closed | 16-05-26
13 | I013 | 13-05-26 | Dashboard – Monthly overview cards and graph not connected to API | High | Aditya B, Swati | Aditya B, Swati | Vaishnavi | Closed | 19-05-26
14 | I014 | 13-05-26 | Create Order – Smart Paste not fetching address | High | Swati | Swati | Vaishnavi | Closed | 15-05-26
15 | I015 | 13-05-26 | Courier Master – Mobile number field missing | High | Aditya B, Swati | Aditya B, Aditya M | Vaishnavi | Closed | 16-05-26
16 | I016 | 13-05-26 | Bulk Upload – Background colour needs to be changed | Low | Aditya B, Swati | Swati | Vaishnavi | Closed | 16-05-26
17 | I017 | 13-05-26 | UI not responsive across screen sizes | High | Swati | Swati, Aditya B | Vaishnavi | Closed | —
18 | I018 | 13-05-26 | Dashboard – Yearly view button missing for graph | High | Swati, Aditya B, Aditya M | Swati | Vaishnavi | Closed | 15-05-26
19 | I019 | 13-05-26 | Dashboard – Date filter missing on overview cards | High | Swati, Aditya B, Aditya M | Swati | Vaishnavi | Closed | 16-05-26
20 | I020 | 13-05-26 | Recent Scans – Page not created; page name needs to be updated | High | Swati | Swati | Vaishnavi | Closed | 20-05-26
21 | I021 | 13-05-26 | Recent Scans – Date filter missing | Medium | Aditya B, Swati, Aditya M | Swati | Vaishnavi | Closed | 15-05-26
22 | I022 | 13-05-26 | Recent Scans – View All button missing | High | Aditya B, Swati | Swati | Vaishnavi | Closed | 15-05-26
23 | I023 | 13-05-26 | Recent Scans – Search bar missing | Medium | Swati | Swati | Vaishnavi | Closed | 25-05-26
24 | I024 | 13-05-26 | Recent Scans – Parcel Status column should be removed | Medium | Swati | Swati | Vaishnavi | Closed | 20-05-26
25 | I025 | 14-05-26 | Dashboard – Graph colour should match corresponding card colour | High | Swati | Swati | Vaishnavi | Closed | 20-05-26
26 | I026 | 14-05-26 | Error toast / alert notification text colour is black; should be white | Low | Swati | Swati | Vaishnavi | Closed | 20-05-26
27 | I027 | 15-05-26 | Create Order – Paid / Unpaid checkbox missing | Medium | Aditya B, Swati, Aditya M | Swati | Vaishnavi | Closed | 16-05-26
28 | I028 | 15-05-26 | Order List – Paid / Unpaid column missing | Medium | Aditya B | — | Vaishnavi | Closed | 20-05-26
29 | I029 | 15-05-26 | Order List – Date filter and Download PDF button missing from action dropdown | Medium | Aditya B, Swati | — | Vaishnavi | Closed | 25-05-26
30 | I030 | 16-05-26 | Product Catalogue – Search not working (frontend wiring issue; backend works) | Low | Swati | Swati | Vaishnavi | Closed | 20-05-26
31 | I031 | 16-05-26 | Bulk Order – LLM helper prompt not precise enough for product matching | High | Aditya B | Aditya B | Vaishnavi | Closed | —
32 | I032 | 16-05-26 | Order List – Cancelled orders should disable all actions and prevent checkbox selection | Medium | Swati | Swati | Vaishnavi | Closed | 20-05-26
33 | I033 | 19-05-26 | Role-based login access control not functioning correctly | High | Aditya B, Swati | Aditya B | Vaishnavi | Closed | 25-05-26
34 | I034 | 19-05-26 | Add Box feature – implementation incomplete | Medium | Aditya B | Aditya B | Vaishnavi | Closed | —
35 | I035 | 21-05-26 | Print Label – QR code not displaying product details after scanning | Medium | Aditya B | Aditya B | Vaishnavi | Closed | —

## App Issues
SDCMS – Mobile App Issue Log (7 Issues — All Closed)
Total: 7 ¦ High: 3 ¦ Medium: 1 ¦ Low: 3 ¦ Status: All Closed
# | Bug ID | Date Reported | Description / Summary | Priority | Assigned To | Fixed By | Reported By | Status | Updated On
1 | IS001 | 20-05-26 | Login Page – Sign In with Employee Code option should be removed | Medium | Aditya B | Aditya B | Vaishnavi | Closed | —
2 | IS002 | 20-05-26 | Login Page – App name needs to be updated | Low | Aditya B | Aditya B | Vaishnavi | Closed | —
3 | IS003 | 20-05-26 | Login Page – Subtitle below Sign In button and 'Developed by Rytnow System' text should be removed | Low | Aditya B | Aditya B | Vaishnavi | Closed | —
4 | IS004 | 20-05-26 | App UI is not responsive across device screen sizes | High | Aditya B | Aditya B | Vaishnavi | Closed | —
5 | IS005 | 20-05-26 | Scan History – History not syncing across devices for the same login account | High | Aditya B | Aditya B | Vaishnavi | Closed | —
6 | IS006 | 20-05-26 | Scan History – Missing fields: Parcel ID, Sender Name, Receiver Name, AWB Number, Courier Service | High | Aditya B | Aditya B | Vaishnavi | Closed | —
7 | IS007 | 25-05-26 | Password reset email displays incorrect company name; should read 'Utsav Creation' | Low | Aditya B | Aditya B | Vaishnavi | Closed | —

## Sign-Off
SIGN-OFF — SDCMS Bug Report
Role | Name | Signature | Date
QA Tester | Vaishnavi
Sr. Developer | Aditya Bachawad
Jr. Developer | Swati
Data Base | Aditya Mulay
Project Manager | Aparna Ma'am